## Sheet1
Task Status | Task Name | Duration | Start | Finish
| Training Phase | 12 Weeks | 2024-01-08 | 16/10/2024
| General Foudation Topics (Cross Teams) | Week 1 - Week 2 | 2024-01-08 | 2024-07-08
Software, Mechanical, and Electrical Basic Concepts
Team Roles and Communication
Safety Protocoles
Software Team
| Introduction to Software & Algorithms | Week 3 | 2024-08-08 | 14/8/2024
- Programming Language & Tools
- Basic Roborics Software Architecture
| Advanced Software Topics | Week 4 | 15/8/2024 | 21/8/2024
- Control Systems and Algorithms
- Robot Vision and Image Processing
- Communication Systems
Mechanical Team
| Mechanical Basics | Week 3 | 2024-08-08 | 14/8/2024
- Introduction to Mechanical Engineering for Robotics
- Materials and Design Considerations
| Advanced Mechanical Topics | Week 4 | 15/8/2024 | 21/8/2024
- Actuators & Kinematics
- Waterproofing & Enclosures
- Prototyping
Electrical/Systems Team
| Electrical Engineering Basis | Week 3 | 2024-08-08 | 14/8/2024
- Introduction to Electricals Systems
- Sensors & Actuators
| Advanced Electrical Systems | Week 4 | 15/8/2024 | 21/8/2024
- Control Systems and Power Management
- Advanced Sensors
| Specific to ROV Competition Preparation | Week 5 - Week 6 | 22/8/2024 | 2024-04-09
Software Team
- Navigation
- Sensor Integration
Mechanical Team
- ROV-Specific Mechanical Design
- Weight Distribution and Buoyancy
Electrical/Systems Team
- Underwater Communication
- Power Supply & Management in Water
| Specific to ROV Competition Preparation | Week 7 - Week 8 | 2024-05-09 | 18/9/2024
Software Team
- Task Automation & Real-Time Control
- Simulations
Mechanical Team
- Propulsion Systems & Thrust
- Task-Specific Mechanical Design
Electrical/Systems Team
- Finalizing Wiring and Power Systems
- Testing Communication Systems
| Review, Refinement, and Mock Challenges | Week 9 -Week 10 | 19/9/2024 | 2024-02-10
Software Team
- Code Review & Refinement
Mechanical Team
- Physical Testing and Refining
Electrical/Systems Team
- Final Integration and System Testing
| Wrap-Up and Final Review | Week 11- Week 12 | 2024-03-10 | 16/10/2024
Team-wide Mock Competition
Final Troubleshooting
| Planning Phase | 2 Weeks | 17/10/2024 | 31/10/2024
Related Work and Prior Solutions
Initial Design and Conceptualization
Software Team
- Review software architecture and requirements
- Set initial software framework for control systems.
- Plan sensor integration (camera, depth sensors, etc.)
- Plan integration of vision and navigation algorithms
- Finalize software architecture for real-time processing
Mechanical Team
- Finalize design and CAD models for ROV
- Select materials and components
- Review and choose thrusters, manipulators, etc
- Refine structural design and perform simultaions
- Finalize frame construction and water-tight seals
Electrical/Systems Team
- Define power management and communication protocols
- Initial planning for wiring system
- Design and prototype power distribution board
- Set up communication systems (acoustic or tethered)
- Confirm motor controllers, battery choices, and wiring needs.
| Prototype Build & Preliminary Testing Phase | 19 Weeks | 2024-01-11 | 2025-09-01
| Frame & Mechanical System Assembly | Week 1 - Week 2 | 2024-01-11 | 14/11/2024
- Assemble the ROV frame based on finalized CAD models.
- Test material durability, buoyancy, and weight distribution.
- Attach thrusters, manipulators, and waterproofing components
- Mechanical stress testing and underwater submersion trials
| Electrical & Power System Setup | Week 3 - Week 4 | 15/11/2024 | 28/11/2024
- Integrate power distribution board, motor controllers, and wiring
- Ensure waterproof electrical housings are properly sealed
- Connect batteries and test power consumption & efficiency
- Test thruster control & response time
| Sensor & Communication Systems Integration | Week 5 - Week 6 | 29/11/2024 | 2024-12-12
- Integrate depth sensors, IMU, and cameras for navigation
- Establish wired/tethered or acoustic communication
- Debug and refine data transmission stability
| Software Development & Testing | Week 7 - Week 8 | 13/12/2024 | 26/12/2024
- Implement real-time control algorithms for navigation & task execution
- Test ROV response with manual and autonomous modes
- Begin simulation tests for object detection & automation
| Initial Underwater Testing & Debugging | Week 9 - Week 10
- Perform full integration tests in controlled water environments
- Identify and fix leaks, signal interference, power issues
- Validate sensor accuracy & camera visibility
| Full System Integration & Advanced Testing |  | 2025-10-01 | 20/2/2025
| Advanced Software Testing & Task Automation | Week 11 - Week 12 | 2025-10-01 | 23/1/2025
- Fine-tune image processing & object detection
- Improve autonomous navigation & sensor-based decision-making
- Integrate manipulator control for mission tasks
| Full Underwater Trials & Stress Testing | Week 13 - Week 14 | 24/1/2025 | 2025-06-02
- Simulate real competition conditions in open water
- Test maneuverability, mission task execution, & endurance
- Optimize energy efficiency and performance stability
| Final Debugging & Redundancy Checks | Week 15 - Week 16 | 2025-07-02 | 20/2/2025
- Debug hardware/software failures under extreme conditions
- Implement backup control systems & fail-safes
- Ensure competition compliance & safety standards
| Final Preparation & Mock Competitions |  | 21/2/2025 | 14/3/2025
| Simulation of Competition Tasks | Week 17 | 21/2/2025 | 27/2/2025
- Conduct mock missions replicating competition tasks
- Evaluate ROV performance under timed conditions
| Transport & Setup Readiness | Week 18 | 28/2/2025 | 2025-06-03
- Ensure ROV packaging, spare parts, & tools are competition-ready
- Conduct final dry and wet runs in different environments
| Final Backup & Last-Minute Adjustments | Week 19 | 2025-07-03 | 14/3/2025
- Perform a final checklist of all systems
- Optimize pilot training & team role coordination
- Travel & register for competition setup & calibration